## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
sprint 1 | sprint-1 | US-01 | As a developer, I want to set up the Python, LangChain, LangGraph and Ollama environment so that the enterprise AI workflow platform can be developed and tested. | MUST HAVE | None | Aruna | 3- Completed
| sprint-1 | US-02 | As a system, I want an Intake Agent to understand and classify different business requests and extract relevant information from them. | MUST HAVE | US-01 | Aruna | 3- Completed
| sprint-1 | US-03 | As a system, I want a Planning Agent to identify the required processing steps for each type of enterprise request. | MUST HAVE | US-02 | Aruna | 3- Completed
| sprint-1 | US-04 | As a system, I want a Coordination Engine to route each classified request to the appropriate enterprise agent such as HR, IT, Finance or Procurement. | MUST HAVE | US-03,US-02 | Aruna | 3- Completed
| sprint-1 | US-05 | As a system, I want specialized enterprise agents to handle domain-specific workflows based on the request type. | MUST HAVE | US-04 | Aruna | 3- Completed
| sprint-1 | US-06 | As a system, I want a Response Agent to generate a clear acknowledgement based on the request, plan and processing result. | MUST HAVE | US-03, US-05 | Aruna | 3- Completed
| sprint-1 | US-07 | As a system, I want LangGraph to connect the agents into an ordered workflow so that information flows between agents. | MUST HAVE | US-02, US-03, US-04 | Aruna | 3- Completed
| sprint-1 | US-08 | As a user, I want a Streamlit interface with separate enterprise-agent sections so that I can interact with and monitor the workflow through a single platform. | SHOULD HAVE | US-07 | Aruna | 3- Completed
| sprint-1 | US-09 | As a developer, I want to perform unit testing and workflow validation to ensure that each agent and the complete workflow work correctly. | SHOULD HAVE | US-07 | Aruna | 3- Completed
sprint 2 | sprint-2 | US-10 | As a system, I want to integrate enterprise tools with the currently supported HR, IT Support and Knowledge services so that employee requests can be processed through the appropriate workflow. | MUST HAVE | US-04 | Aruna | 3- Completed
| sprint-2 | US-11 | As a system, I want to dynamically select and execute the required tools based on the user's request and pass the required information to them. | MUST HAVE | US-10 | Aruna | 3- Completed
| sprint-2 | US-12 | As a system, I want to validate tool results and make an intelligent decision such as continue, information, human review or confirmation. | MUST HAVE | US-11 | Aruna | 3- Completed
| sprint-2 | US-13 | As a system, I want to support multiple agents and multiple tools for complex enterprise requests. | SHOULD HAVE | US-11,12 | Aruna | 3- Completed
| sprint-2 | US-14 |  | SHOULD HAVE | US-12 | Aruna | 3- Completed
sprint 3 | sprint 3 | US-15 | As a system, I want to provide secure company and employee authentication so that employee data is accessed only by authorized users. | MUST HAVE | US-15 | Aruna | 3- Completed
| sprint 3 | US-16 | As an employee, I want to manage my projects, modules and milestones so that my work progress can be maintained in the platform. | MUST HAVE | US-15 | Aruna | 3- Completed
| sprint 3 | US-17 | As an employee, I want to view my achievements, participations and performance information so that my work history is available in one place. | MUST HAVE | US-16 | Aruna | 3- Completed
| sprint 3 | US-18 | As an employee, I want to upload, download and delete project files so that my project documents can be managed securely. | SHOULD HAVE | US-16 | Aruna | 3- Completed
| sprint 3 | US-19 | As a system, I want to use employee context and memory in workflow processing so that responses can be personalized. | SHOULD HAVE | US-15 | Aruna | 3- Completed
sprint 3
Sprint 4 & 5 | sprint 4 & 5 | US-20 | As an employee, I want the AI Coordinator to understand HR and IT support requests, ask for missing details, and route them to the correct service. | MUST HAVE | US-04, US-12 | Aruna | In Progress
Sprint 4 & 5 | sprint 4 & 5 | US-21 | As a system, I want workflow steps, tool results, and decisions to be validated so that actions requiring employee confirmation are not executed prematurely. | MUST HAVE | US-20 | Aruna | In Progress
Sprint 4 & 5 | sprint 4 & 5 | US-22 | As an employee, I want to review request details and confirm before an action is executed, and then see its status and history. | MUST HAVE | US-21 | Aruna | In Progress
Sprint 4 & 5 | sprint 4 & 5 | US-23 | As an administrator, I want a dashboard to monitor HR and IT support requests, workflow status, and decisions. | MUST HAVE | US-20, US-21 | Aruna | In Progress
Sprint 4 & 5 | sprint 4 & 5 | US-24 | As a system, I want REST API endpoints for workflow execution and agent interaction so that the platform can integrate with other systems. | SHOULD HAVE | US-20, US-21 | Aruna | In Progress
Sprint 4 & 5 | sprint 4 & 5 | US-25 | As a developer, I want end-to-end testing, logging, error handling, and deployment documentation so that the final platform can be demonstrated reliably. | MUST HAVE | US-22, US-23, US-24 | Aruna | In Progress
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours. Sprint 3 completed on Oct 5, 2026; combined Modules 4 & 5 final phase runs Oct 6–12, 2026.
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T - 01 | Set up Python virtual environment and install required dependencies. | 2026-08-31 | 2026-08-31 | Aruna | Environment Setup | 3- Completed
US-01 | T-02 | Configure LangChain, LangGraph and Ollama for local LLM processing. | 2026-08-31 | 2026-08-31 | Aruna | Configuration | 3- Completed
US-02 | T-03 | Design WorkflowState and implement the Intake Agent. | 2026-08-31 | 2026-09-01 | Aruna | Agent Development | 3- Completed
US-02 | T-04 | Test request classification and extraction for different business requests. | 2026-09-01 | 2026-09-01 | Aruna | Testing | 3- Completed
US-03 | T-05 | Implement Planning Agent with workflow steps for different request types. | 2026-09-01 | 2026-09-01 | Aruna | Agent Developmen | 3- Completed
US-04 | T-06 | Implement Response Agent to generate context-aware acknowledgement responses. | 2026-09-01 | 2026-09-02 | Aruna | Agent Developmen | 3- Completed
US-05 | T-07 | Build LangGraph workflow connecting Intake, Planning and Response Agents. | 2026-09-02 | 2026-09-02 | Aruna | Workflow Integration | 3- Completed
US-06 | T-08 | Integrate Ollama with the agent workflow and verify local LLM responses. | 31-Sep-26 | 2026-09-02 | Aruna | LLM Integration | 3- Completed
US-07 | T-09 | Implement CLI to accept user input and display classification, details, plan and response. | 2026-09-02 | 2026-09-02 | Aruna | CLI Development | 3- Completed
US-08 | T-10 | Perform end-to-end workflow validation using leave, equipment, IT support and reimbursement requests. | 2026-09-02 | 2026-09-02 | Aruna | Validation | 3- Completed
US-09 | T-11 | Create and integrate the centralized enterprise tool registry for HR, IT, Procurement, Finance, Recruitment and Knowledge tools. | 2026-09-03 | 2026-09-03 | Aruna | Tool Integration | 3- Completed
US-10 | T-12 | Implement dynamic tool selection and execution based on AI-generated request analysis and tool plans. | 2026-09-06 | 2026-09-04 | Aruna | Tool Execution | 3- Completed
US-11 | T-13 | Implement tool-result validation, confirmation handling and Decision Engine for enterprise actions. | 2026-09-21 | 2026-09-05 | Aruna | Validation & Decision | 3- Completed
US-12 | T-14 | Test multi-agent and multi-tool requests and improve incorrect tool or agent selection. | 2026-09-22 | 2026-09-06 | Aruna | Integration Testing | 3- Completed
US-13 | T-15 | Improve the chatbot interface to display conversation history, workflow execution trace, selected agents, tools used, validation results, and final responses. | 2026-09-26 | 2026-09-07 | Aruna | UI Development | 3- Completed
US-14 | T-16 | Implement company and employee authentication with secure access control. | 2026-09-28 | 2026-09-29 | Aruna | Authentication | 3- Completed
US-15 | T-17 | Develop employee project management with project details, modules and milestones. | 2026-09-29 | 2026-09-30 | Aruna | Portfolio Development | 3- Completed
US-16 | T-18 | Integrate employee achievements, participations and performance information. | 2026-09-30 | 2026-10-01 | Aruna | Employee Management | 3- Completed
US-17 | T-19 | Implement project file upload, download and delete functionality with ownership validation. | 2026-10-01 | 2026-10-02 | Aruna | File Management | 3- Completed
US-18 | T-20 | ntegrate short-term conversation memory and long-term employee preferences. | 2026-10-02 | 2026-10-03 | Aruna | Memory Integration | 3- Completed
US-19 | T-21 | Register and integrate the employee portfolio service with the workflow architecture. | 2026-10-03 | 2026-10-04 | Aruna | Tool Integration | 3- Completed
US-20 | T-22 | Perform end-to-end testing of authentication, portfolio, performance and workflow modules. | 2026-10-04 | 2026-10-05 | Aruna | Integration Testing | 3- Completed
US-20 | T-23 | Integrate the AI Coordinator with the currently supported HR, IT Support and Knowledge services; verify request routing. | 2026-10-06 | 2026-10-06 | Aruna | Agent Coordination | In Progress
US-20 | T-24 | Test natural-language HR and IT requests and ensure missing details are collected before processing. | 2026-10-06 | 2026-10-07 | Aruna | Workflow Testing | In Progress
US-21 | T-25 | Add workflow-result validation and decision handling for continue, request-more-information, confirmation and human review. | 2026-10-07 | 2026-10-08 | Aruna | Decision Intelligence | In Progress
US-22 | T-26 | Implement employee review and explicit confirmation before protected actions; show status and request history. | 2026-10-08 | 2026-10-09 | Aruna | Employee Workflow | In Progress
US-23 | T-27 | Complete the admin dashboard for monitoring HR and IT support requests, workflow progress and decisions. | 2026-10-09 | 2026-10-10 | Aruna | Dashboard Development | In Progress
US-24 | T-28 | Implement and verify REST API endpoints for workflow execution and agent interaction where supported by the project. | 2026-10-10 | 2026-10-11 | Aruna | API Development | In Progress
US-25 | T-29 | Run end-to-end tests, fix high-priority issues, verify logging/error handling, and prepare final run/deployment instructions. | 2026-10-11 | 2026-10-12 | Aruna | Integration Testing & Release | In Progress
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
sprint 1 | 2026-08-31 | No major blockers. Initial setup and Ollama configuration were being completed. | Completed the project environment setup and started development of the agent foundation
sprint 1 | 2026-09-01 | Intake classification and response generation required testing with different request types. | Tested leave, equipment, IT support and reimbursement requests and refined the agent prompts.
sprint 1 | 2026-09-02 | End-to-end integration and CLI validation remained. | Connected the workflow using LangGraph, completed CLI testing and validated the complete Module 1 workflow.
sprint 2 | 2026-09-03 | Enterprise tools needed a common structure. | Integrated tools through a centralized tool registry.
sprint 2 | 2026-09-05 | Some requests selected incorrect or generic tools. | Improved AI-based agent and tool selection.
sprint 2 | 2026-09-10 | Tool results needed verification before final response. | Added validation and decision handling.
sprint 2 | 2026-09-12 | Complex requests may require multiple agents and tools. | Tested and integrated multi-agent/tool execution.
sprint 2 | 2026-09-24 | Workflow details were not clearly visible in the UI. | Improved chatbot interface and workflow trace display.
sprint 3 | 2026-09-28 | Company and employee data needed secure integration. | Added company-based authentication and employee-specific access control.
sprint 3 | 2026-09-30 | Employee project information needed proper management. | Added projects, modules, milestones, achievements and performance records.
sprint 3 | 2026-10-03 | Project documents needed secure storage and management. | Added project file upload, download and delete functionality.
sprint 3 | 2026-10-05 | End-to-end integration required testing across modules. | Tested authentication, portfolio, performance and workflow execution together.
Sprint 4 & 5 | 2026-10-06 | HR and IT workflows needed final integration with the coordinator. | Integrated service routing and began testing natural-language requests.
Sprint 4 & 5 | 2026-10-07 | Missing details and inconsistent tool outputs needed stronger validation. | Tested information collection and added validation checks.
Sprint 4 & 5 | 2026-10-08 | Actions must not run before the employee reviews and confirms them. | Validated the decision flow for confirmation and human review.
Sprint 4 & 5 | 2026-10-09 | Employee request status and history needed clear visibility. | Connected request outcomes with the employee-facing status/history view.
Sprint 4 & 5 | 2026-10-10 | Administrators needed visibility into active HR and IT support workflows. | Completed dashboard monitoring checks for request and workflow status.
Sprint 4 & 5 | 2026-10-11 | API and end-to-end behaviour required final verification. | Verified supported API paths and tested the integrated workflow.
Sprint 4 & 5 | 2026-10-12 | Final regression checks and handover documentation remained. | Completed final integration checks and prepared project handover instructions.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | sprint 1 | 2026-08-31 | 2026-09-02 | Aruna | Start testing agents with varied business requests. | Stop depending only on predefined examples. | Continue developing generic agents. | Added varied business requests for testing.
2 | sprint 1 | 2026-08-31 | 2026-09-02 | Aruna | Start documenting agent behaviour while developing. | Stop waiting until the end to test. | Continue testing each agent separately. | Recorded errors and tested agents incrementally.
3 | sprint 1 | 2026-08-31 | 2026-09-02 | Aruna | Start checking extracted details carefully. | Stop accepting incorrect outputs without checking. | Continue using fallback handling for reliability. | Checked classification, extraction and fallback behaviour.
4 | sprint 1 | 2026-08-31 | 2026-09-02 | Aruna | Start checking the complete workflow after integration. | Stop treating individual agent testing as sufficient. | Continue integrating Intake, Planning and Response agents. | Successfully tested the complete CLI workflow with different requests.
5 | sprint 2 | 2026-09-03 | 2026-09-24 | Aruna | Test tools with varied enterprise requests. | Stop depending on fixed examples. | Continue dynamic AI-based processing. | Tested HR, IT and Procurement requests.
6 | sprint 2 | 2026-09-04 | 2026-09-25 | Aruna | Validate tool results before responding. | Stop assuming every execution is successful. | Continue using validation and Decision Engine | Added result validation.
7 | sprint 2 | 2026-09-05 | 2026-09-26 | Aruna | Test multiple tools and agents together. | Stop testing only simple requests. | Continue improving coordination. | Tested complex enterprise requests.
8 | sprint 2 | 2026-09-06 | 2026-09-27 | Aruna | Improve UI transparency. | Stop hiding workflow execution details. | Continue improving chatbot experience. | Added agent, tool, validation and decision details.
9 | sprint 2 | 2026-09-07 | 2026-09-28 | Aruna | Prepare tools for future company integration. | Stop treating mock data as final. | Continue modular tool development. | Structured tools so they can later connect to company APIs/DBs.
10 | sprint 3 | 2026-09-28 | 2026-10-05 | Aruna | Start testing company and employee-specific workflows. | Stop using only common demo data. | Continue developing secure enterprise workflows. | Tested workflows using company and employee context.
11 | sprint 3 | 2026-09-28 | 2026-10-05 | Aruna | Start implementing employee portfolio features. | Stop keeping project information outside the system. | Continue building employee-focused features. | Added projects, modules, milestones, achievements and performance records.
12 | sprint 3 | 2026-09-28 | 2026-10-05 | Aruna | Start validating employee data access. | Stop allowing unauthorized employee data access. | Continue using company and employee-level authorization. | Implemented company ID and employee ID based access control.
13 | sprint 3 | 2026-09-28 | 2026-10-05 | Aruna | Start managing project documents within the system. | Stop storing project files without ownership validation. | Continue improving project management. | Added project file upload, download and delete functionality.
14 | sprint 3 | 2026-09-28 | 2026-10-05 | Aruna | Start using memory for personalized workflows. | Stop treating every request independently. | Continue improving intelligent workflow processing. | Added short-term conversation memory and long-term employee preferences.
15 | sprint 3 | 2026-09-28 | 2026-10-05 | Aruna | Start testing natural-language employee requests. | Stop depending only on fixed commands. | Continue improving chatbot interaction. | Integrated chatbot requests with the enterprise workflow system.
16 | sprint 3 | 2026-09-28 | 2026-10-05 | Aruna | Start performing complete end-to-end testing. | Stop considering individual module testing as sufficient. | Continue improving agent and tool coordination. | Tested authentication, portfolio, performance, projects and workflow execution together.
18 | Sprint 4 & 5 | 2026-10-06 | 2026-10-12 | Aruna | Start validating service routing with realistic HR and IT requests. | Stop treating a successful individual tool call as proof of end-to-end success. | Continue using modular agents and shared company knowledge. | Integrated and tested HR, IT Support and Knowledge routing.
19 | Sprint 4 & 5 | 2026-10-06 | 2026-10-12 | Aruna | Start checking confirmation gates and missing-information paths. | Stop executing protected actions before explicit confirmation. | Continue validating decisions before presenting final results. | Checked confirmation, information-request and human-review paths.
20 | Sprint 4 & 5 | 2026-10-06 | 2026-10-12 | Aruna | Start monitoring workflow status from employee and admin views. | Stop leaving request outcomes unclear to users. | Continue improving status visibility and history. | Verified request status/history and admin monitoring.
21 | Sprint 4 & 5 | 2026-10-06 | 2026-10-12 | Aruna | Start running final end-to-end regression tests before handover. | Stop relying on isolated module checks only. | Continue documenting setup and known limitations. | Completed final integration checks and prepared run/deployment guidance.